
Consolidated Environmental Action Plan

Ballarpur Industries Ltd.
The BORROWER commits itself to the actions as specified below, within the specified deadlines, and declares that the resources specified below have been allocated.
	Plant
	Issue
	Task
	Responsible Staff
	Target Completion Date

	Ballarpur
	Air emissions
	Install ESP on boilers 4 & 6 and on recovery boiler

Install lime kiln

Install scrubbers and incinerators for bleach plant vapors and NCG


	Mr. S.K. Khurana
	December 2004

April 2005

June 2006

	
	Liquid effluents
	Full conversion to Elemental chlorine-free production (ECF)

Install oxygen de-lignification

Install filters for fiber recovery

Complete upgrade of effluent treatment plant


	“
	December 2007
June 2005

June 2005

June 2005

	
	Environmental Management System
	Achieve ISO 14001 certification for EMS


	“
	June 2004

	
	General Housekeeping
	Improve general housekeeping (to benchmark standard achieved at BGPL)


	“
	December 2004

	
	Occupation Health and Safety
	Improve workplace safety and employee utilization of personal protective equipment (to benchmark  standard achieved at BGPL)


	“
	December 2004

	
	
	
	
	

	APR
	Air emissions
	Install ESP on power boilers

Upgrade of ESP on recovery boiler

Upgrade lime kiln to control particulate emissions

Install scrubbers and incinerators for bleach plant vapors and NCG


	Mr. S.K. Khurana
	December 2004

December 2004

December 2004

June 2006

	
	Liquid effluents
	Complete upgrade of effluent treatment plant
	“
	September 2005

	
	Environmental Management System


	Achieve ISO 14001 certification for EMS
	“
	September 2004

	
	General Housekeeping
	Improve general housekeeping (to benchmark standard achieved at BGPL)


	“
	December 2004

	
	Occupation Health and Safety
	Improve workplace safety and employee utilization of personal protective equipment (to benchmark  standard achieved at BGPL)


	“
	December 2004

	
	
	
	
	

	SEWA
	Air emissions
	Upgrade of ESP’s on power and recovery boilers

Install scrubbers and incinerators for bleach plant vapors and NCG

Install lime kiln
	Mr. S.K. Khurana
	December 2004

September 2006

September 2006



	
	Liquid effluents
	Full conversion to ECF production

Complete upgrade of effluent treatment plant

Install filters for fiber recovery
	“
	December 2008

December 2004

September 2005



	
	Environmental Management System
	Achieve ISO 14001 certification for EMS


	“
	September 2004

	
	General Housekeeping
	Improve general housekeeping (to benchmark standard achieved at BGPL)


	“
	December 2004

	
	Occupation Health and Safety
	Improve workplace safety and employee utilization of personal protective equipment (to benchmark  standard achieved at BGPL)


	“
	December 2004

	
	
	
	
	

	Shree

Gopal
	Air emissions
	Upgrade of ESP’s on power and recovery boilers

Installation of incinerators for bleach plant vapors and NCG

Install lime kiln (relocated from APR)


	Mr. S.K. Khurana
	December 2004

June 2006

April 2004

	
	Liquid effluents
	Full conversion to ECF production

Complete upgrade of effluent treatment plant 

Install filters for fiber recovery
	“
	December 2005

June 2005

June 2005



	
	Environmental Management System


	Achieve ISO 14001 certification for EMS
	“
	June 2004

	
	General Housekeeping
	Improve general housekeeping (to benchmark standard achieved at BGPL)


	“
	December 2004

	
	Occupation Health and Safety
	Improve workplace safety and employee utilization of personal protective equipment (to benchmark  standard achieved at BGPL)


	“
	December 2004


REnglish
F:\Richard English\INDIA PROJECTS\Pipeline\BILT II  20798\BILT Consolidated  EAP_Final.doc
November 6, 2003 2:42 PM
Ballarpur Industries Ltd. Consolidated Environmental Action Plan







2

