## Sheet1
Stora China III (IFC Reference # 27286)
Environmental and Social Action Plan (ESAP)
Action | Completion Date
PS1: Assessment and Management of Environmental and Social Risks and Impacts
1. Demonstrate that each contractor in relation to the forestry operations is in material compliance with the Stora Enso Group sustainability requirements, as defined in the work instructions, standard operating procedures and Integrated Operational Site Planning Documents (IOSP), through the following actions:
(i) reviewing the inclusion of sustainability criteria in road construction, harvesting and replanting work instructions and the IOSP and other operational documents; | (i) 2014.02.28
(ii) including ongoing monitoring results in the contractor performance and selection system; | (ii) Submitted as part of each Annual Monitoring Report (AMR)
(iii) regular contractor compliance trends monitoring reviewed semi-annually | (iii) Submitted as part of each AMR
(iv) addressing contractor deficiencies through contractor development and training plan; and | (iv) Compliance results and training report submitted in each AMR
(v) reviewing and revising performance-based clauses in the contractor agreements as needed. | (v) As needed and agreed between the Forestry Companies and IFC
2. Maintain ISO9001 / ISO14001 / OHSAS18001 and FSC Sustainable Forest Management certifications for the forestry operation, and traceability systems verifying legal origin of wood | Forestry Annual external audit results included in each AMR.
3. (i) Develop and implement a program of environmental and social (E&S) impact monitoring and regular public reporting of key sustainability parameters related to both the forestry and the mill operations. Undertake regular public reporting of the agreed key parameters to local stakeholders, using project sustainability newsletters and other locally appropriate means. | (i) Monitoring results and evidence of public reporting captured in each AMR.
(ii) Undertake a review of the mill project’s community grievance mechanisms, and reinforce as needed based on review results. Publicly disclose the formal grievance mechanisms to project affected communities. | (ii) Review results available by 2013.12.31; evidence of public disclosure by 2014.01.31.
4. Annual reporting to local affected stakeholders of the status of the implementation of the items listed in this ESAP which address risks or impacts or are issues of concern to affected stakeholders.
(i) Identify an appropriate means for communicating the reporting and align this with what is otherwise defined for the respective item in this ESAP. | (i) Communication plan presented to IFC for this information, by 2014.02.28
(ii) Annual reporting on relevant ESAP items implemented. | (ii) Evidence of public reporting captured in each AMR.
PS2: Labor and Working Conditions
5. The Project Companies shall contractually require plantation and mill contractors and their subcontractors to employ workers on terms compliant with the law, applicable Stora Enso policies and procedures and applicable requirements of PS2. These provisions (including those related to the protection of ethnic minority workers) shall be incorporated into any future or renewed contracts and such provisions will be adopted by Project contractors.
(i) Develop appropriate procedures for monitoring compliance and incorporate such procedures into the relevant management plans. | (i) Management plans for Forestry and Mill Construction available by: 2014.02.28. Management plan for Mill Operation available 6 months prior to the start of operation
(ii) Report monitoring results of contractor compliance in each AMR for (a) the forestry operations and wood transport, (b) the mill construction; (c) the mill operations; and (d) contractor accommodation. | (ii) Reporting: a. Forestry operations – first report included in first AMR after commitment; thereafter included in subsequent AMRs.
b. Mill construction – first report within 6 months of commitment; bi-annually thereafter until completion of construction;
c. Mill operations – first report included in first AMR after mill start up; thereafter included in subsequent AMRs.
d. Contractor accommodation – first report within 6 months of commitment; bi-annually thereafter until completion of construction
6. OHSAS18001 certification for the mill operations.
(i) Attain OHSAS18001 certification for the mill operations. | (i) OHSAS18001 attained two years after the start of commercial production.
(ii) Monitor and report on OHS statistics based on the standardized common Stora Enso corporate procedures and definitions. | (ii) Submitted as part of each AMR
PS3: Resource Efficiency and Pollution Prevention
7. Develop the capability to assess and incorporate into operations the risks and impacts of the forestry operations on water quality and quantity, through the following measures:
(i) review and develop a strategy for assessing potential impacts of the forestry operations on surface water; and | (i) 2014.12.31
(ii) incorporate results from the Forestry Companies’ own surface water monitoring trials and/or surface water monitoring trials elsewhere in comparable conditions into the forestry management work instructions / standard operating procedures and into IOSP. Provide IFC with updated guidelines. | (ii) Within AMRs starting in 2015.
8. For the forestry operations, ensure ongoing monitoring of soil loss and fertility management and adapt the IOSP on the basis of the monitoring results:
(i) monitoring plan for calibration of forest management practices with soil loss finalized and submitted to IFC for review and comment; | (i) 2014.12.31
(ii) periodic review of soil erosion monitoring results provided; and | (ii) Included as part of AMR; first review included in AMR submitted in 2015
(iii) Implement a process to evaluate what is learned from the ongoing monitoring of soil loss and incorporate those learnings into revised sustainability requirements in IOSP and road building, wood harvest and silviculture guidelines. | (iii) Evaluation results, and revised IOSP (as needed) included in subsequent AMRs
PS4: Community Health, Safety and Security
9. Public health information program applicable to mill construction and operations: | Deliveries as per below:
Develop and implement a local affected community and worker health information program with a focus on preventing communicable diseases). Program details will be communicated with local affected communities and workers including contractor and sub-contractor workers.
(i) Program key content and communication plan delivered before first disbursement. | (i) 2014.02.28
(ii) Verification through communication records semi-annually related to construction period activities. | (ii) Within AMRs starting in 2014.
10. Management of Safety Risk in Road Transport:
Each Project Company, will in relation to the mill and forest operations, plan and implement management procedures to ensure that its own transport services and any contracted transport services, including wood transport, to and from locations in Guangxi connected with the Project are performed in a safe way by its own employees and any contractor employees (including their sub-contractors).
(i) Define safety requirements and guidelines for transport. | (i) Submitted by 2014.02.28
(ii) Include the developed safety requirements into new transport services contracts. | (ii) Submitted by 2014.02.28
(iii) Establish a program to monitor safety in road transport which is reported in AMR | (iii) Submitted by 2014.02.28
PS5: Land Acquisition and Involuntary Resettlement
11. Social Land Monitoring;
(i) Use an internal system of the Forestry Companies to track, investigate, and on Existing Social Land and Additional Social Land (as needed) address the following: (a) the involvement of intermediate social land lease parties; (b) the difference between the rent paid by the Forestry Companies and the rent received by the primary land use right holders for the contracted land; | (i) Tracking results included in AMR
(ii) Assessment by a qualified external expert of the system level implementation on Existing Social Land of the internal tracking system and related procedures, standards, and policies as referred to in clause (i) above. | (ii) External assessment report available by 2014.09.31
12. Mill Site Resettlement
(i) Monitor the progress of the resettlement action plan against the intermediate milestone objectives and indicators. This shall be verified by semi-annual internalreports. Adapt the resettlement action plan, in agreement with affected communities, as this monitoring shows necessary, to maximize the plan’s effectiveness in delivering its agreed objectives. | (i) Semi-annual internal monitoring report from 2013.12.31
(ii) The resettlement action plan objectives within the Project Company’s control are substantially reached. Whether such resettlement action plan objectives have been substantially reached will be verified by results of a completion audit conducted by a qualified external social consultant appointed by the Project Companies. | (ii) Completion audit report by 2016.03.31
PS6: Biodiversity Conservation & Sustainable Management of Living Natural Resources
13. High Conservation Value Forest (HCVF)identified and managed accordingly.
(i) Effective conservation and management of HCVF will be assessed through internal management systems and the annual FSC review process. | (i) The FSC FM annual surveillance audit report issued by the Certification Body is provided to IFC – as soon as available and a summary is published on the FSC site.
PS7: Indigenous Peoples
24. As needed based on “Guangxi Stora Enso Forestry Project – Forest Area Ethnic Minorities Livelihood and Rights Protection Research Report” findings.
(i) Perform an internal review and update of the Stakeholder Engagement Plan (SEP) to include provisions to engage local ethnic groups (including ethnic minority contractor and sub-contractor workers) in a culturally appropriate manner | (i) SEP and CDP provided to IFC by 2014.03.31
(ii) Where adverse impacts are identified, ensure ongoing free, prior, and informed consultation (FPIC) with identified ethnic minority groups. This shall be verified through review by a qualified external expert. | (ii) As needed external review report including FPIC consultation records included as annex to the first AMR submitted after first disbursement.