## Sheet1
Task Title/Description | Anticipated Completion Date
Performance Standard 1: Social and Environmental Assessment and Management Systems
1a) Incorporate IFC Performance Standards and the relevant elements of the applicable IFC Environmental, Health and Safety (EHS) guidelines into the corporate Health Safety Environment and Social Responsibility (HSESR) Management System covering: (i) social and environmental assessment, (ii) management program, (iii) organizational capacity, (iv) training, (v) community engagement, (vi) monitoring and (vii) reporting. | 2012-12-01
1b) KEC to i) review applicability of remaining OSL procedures, ii) develop an action and transition plan and iii) close out actions. | 2012-12-01
1c) KEC to undertake review of the corporate HSESR management system to i) ensure IFC’s Performance Standards are fully covered and explicitly defined within the HSESR management system and ii) formalize KEC mine and unexploded ordinance requirements in HSESR management system consistent with good international industry practice. | 2012-12-01
1d) Develop corporate HSESR audit protocol for new acquisitions and audits. Conduct HSESR audits for each KEC acquired operating asset in Egypt and Yemen (and assets where activities have begun) and address audit findings. Audits will consider HSE issues in relation to KEC and contractor activities against KEC policies and procedures and IFC Performance Standards and applicable guidelines . | Complete
1e) Conduct Environmental and Social Impact Assessments in accordance with PS1 (paragraphs 4-12), for exploration assets where ESIAs have not been conducted. | Complete
1f) Hire a corporate HSESR Manager who will advise, coordinate and monitor all HSESR issues across KEC’s operations. | Complete
1g) Hire an HSESR country manager for Yemen and field level HSESR coordinators to support the HSESR country managers in Egypt, Yemen and Ukraine. | Complete
1h) Assign individual and department to oversee Social management aspects of the KEC portfolio | 2012-05-01
1i) Develop and implement a Stakeholder Engagement Plan (SEP) that contains consultation and disclosure procedures that comply with KEC policies and procedures and IFC Performance Standards . | Complete
1j) Develop grievance mechanism to be communicated locally to potentially affected communities that contains complaints procedure clearly indicating who is responsible for receiving complaints; processes followed for recording and acting on complaints; and process for following through, communicating and closing complaints. | Complete
1k) Develop corporate level HSESR awareness training program for implementation across all assets in Egypt, Yemen and Ukraine. | Complete
1l) Implement corporate HSESR Management System for operations in Egypt, Yemen and Ukraine. | Complete
Performance Standard 2: Labor and Working Conditions
2a) Incorporate all requirements of IFC PS2 into the corporate Human Resource Policy and Manual. | 2012-12-01
2b) Implement routine workplace monitoring of air quality, drinking water quality and noise in line with IFC’s EHS General Guidelines. | Complete
Performance Standard 3: Pollution prevention and Abatement
3a) Conduct waste management options assessment that will identify the type and quantity of all waste streams generated at KEC’s assets in Egypt and Yemen. The assessment will consider current methods as well as alternative and available treatment, reuse and disposal routes for these wastes. | Complete
3b) Develop project and site specific waste management plan using results of waste management options assessment (3a above). | Complete
3c) Conduct air emissions and effluent control, management and monitoring assessment for all KEC Egypt assets in accordance with IFC’s EHS Guidelines for Onshore Oil and Gas Development and General EHS Guidelines. Assessment should consider all possible options to flaring associated gas at all producing assets; and alternatives to produced water disposal at all producing assets (e.g. reinjection). Implement required measures in compliance with applicable IFC EHS guidelines. | 2013-01-01
3d) Develop air emissions and effluent monitoring program that adequately demonstrates the effectiveness of KEC’s emissions and effluent control strategies. | Complete
3e) Develop specific oil and chemical spill contingency plan that will document spill prevention measures and spill response measures in relation to KEC’s activities. Field specific plans will address potential oil, chemical and fuel spills from facilities, transport vehicles and loading and unloading operations. The plan should include the contents outlined in IFC’s EHS Guidelines for Onshore Oil and Gas Development. | Complete
3f) Reach a formal collaborative agreement with the relevant authorities in Egypt to determine specific actions, roles, and responsibilities for the clean-up and remediation of oil spill contaminated areas as a result of previous operators in the fields. | Complete
Performance Standard 4: Community Health, Safety and Security
4) Develop security plan and procedures for Yemen operations that ensures security of facilities and personnel using an appropriate level of security cover. Procedures will include standard contractual provisions (e.g. training requirements) to ensure appropriate conduct of security personnel. | Complete
Performance Standard 5: Land Acquisition and Involuntary Resettlement
5) Develop land acquisition and compensation plan as part of corporate land acquisition process that shall be in line with IFC PS5. Plan will include Company policy and procedures for all necessary land acquisition, reinstatement and compensation to land owners and any other land users who are physically or economically displaced. | 2012-10-01
Performance Standard 6: Biodiversity Conservation and Sustainable Natural Resource Management
6) Develop specific bird protection measures in the Area A fields in Egypt. Access expert opinions through consultation with appropriate bodies. | 2012-10-01
Performance Standard 7: Indigenous Peoples
7) If assessments indicate presence of indigenous peoples near KEC operational areas, appropriate mitigation measures and benefit sharing mechanisms will be developed, in accordance with the provisions of PS7. | To be decided in consultation with IFC
Performance Standard 8: Cultural Heritage
8) If assessments indicate a risk to cultural heritage in KEC operational areas appropriate mitigation measures will be developed in accordance with the provisions of PS8. | To be decided in consultation with IFC