## Sheet1
ESAP TUXPAN 32817
Assessment and Management of Environmental and Social Risks and Impacts
Engage a qualified full-time ESHS professional to supervise ESHS management during site preparation and construction activities. | 3 months after disbursement
Develop and implement a Grievance Redress Procedure in line with IFC requirements to receive, register and monitor complaints, claims and suggestions from project-affected people. | 3 months after disbursement
Carry out quarterly independent EHS audits of site preparation and construction activities in alignment with IFC’s General and Sector Specific EHS Guidelines. | Quarterly once Site Preparation Activities begin
Labor and Working Conditions
Prepare a Human Resources Policy aligned with PS2 to clearly define the rights and obligations of employees and the employer regarding compensation and benefits, working hours, occupational health and safety, grievance redress procedures, among others. | 3 months after disbursement
Community Health, Safety and Security
Develop a Traffic Management Plan for the operations phase of the Project to establish safe driving requirements including speed limits, inspection requirements, signage, training requirements for drivers, dust control activities, among others. | Prior to the start of Operational Activities
Biodiversity Conservation and Sustainable Management of Living Natural Resources
Submit a Mangrove Management and Monitoring Program with support from a recognized biodiversity institution or consultant which includes all commitments established in the MIA-R and monitoring requirements to measure the effectiveness of the mitigation measures established | 3 months after disbursement