## Sheet1
Description of the Action Item | Anticipated Completion Date
Performance Standard 1: Assessment and Management of Environmental and Social Risks and Impacts
Tsemex will adopt Key Performance Indicators (KPIs) to mainstream EHS parameters, including: a) Safety – Injury Frequency Rate (Number of injuries per days hours worked) – during construction and Number of incidents per month during operation); b) Water Usage (L/guest/month) and Efficiency – Consumed/guest; Energy Usage (kWh/guest/month) ; Wastewater monitoring; Gas and Diesel consumption/guest/month;c) Waste volumes/month and waste recycled (t/month) d) Staff - Retention and e) Staff Training days. | a) – e) 30 June 2016 (no more than six months after commissioning )
Performance Standard 2: Labor and Working Conditions
Tsemex will develop and implement Human Resources Policies and Procedures appropriate for its workforce that sets out the approach to managing workers consistent with the requirements of Performance Standard 2, IHG guidelines and Ethiopian Labor Law. a) Provide a copy of the HR policies and procedures to IFC for review and approval. | a) 30 September 2015 Three months prior to hotel commissioning
Performance Standard 3: Resource Efficiency and Pollution Prevention
Tsemex will compile a waste management plan, which will give details of how waste is to be minimized, separated and disposed during the operational phase | 30 January 2016 Upon hotel commissioning
Tsemex will compile and implement a pest control and management procedure that is consistent with the WBG General EHS Guidelines. | 30 January 2016 Upon hotel commissioning
Performance Standard 4: Community Health, Safety and Security
Tsemex will implement water treatment and monitoring to comply with WBG General EHS Guidelines for drinking water. | 30 January 2016 Upon hotel commissioning
Tsemex will : (a) apply the HACCP (Hazard Analysis, Critical Control Points) system, or equivalent, in the hotel kitchen, and implement food safety training, monitoring and hygiene practices. (b) compile a comprehensive Fire and Life safety plan in accordance with an internationally recognized standard, with appropriate procedures for both construction and operation phases, and carry out a verification of the adherence to the chosen standard before commissioning; (c) adopt a formal Stakeholder Engagement Plan incorporating a Community Grievance Mechanism as part of its EMS (see PS1 above). | 30 January 2016 Upon hotel commissioning