## ESAP
Environmental and Social (E&S) Action Plan
| Project Name: Landmark Myanmar | IFC Project ID: 33428
Country: Myanmar
No. and PS | Task Title/Description | Completion Date
1/PS1 | Yoma will provide monitoring reports to confirm control of the potential spread of asbestos dust during demolition. Completion indicator: Asbestos monitoring reports available. | Within 1 month of the completion of each demolition phase
2/PS1 | Yoma will develop and adopt a corporate level E&S management system (“ESMS”). This will include: a) an E&S policy and mission statement; b) specific Standard Operating Procedures on but not be limited to the following: E&S screening and due diligence of potential projects; labor and working conditions; occupational health and safety; land acquisition, resettlement, and livelihood restoration; stakeholder engagement and community grievance mechanisms; emergency preparedness and response; E&S requirements on contractors, sub-contractors, and primary suppliers; biodiversity management; resource efficiency and waste management; c) relevant key performance indicators, training programs, and corporate monitoring and reporting programs. d) mechanisms to regularly review ESMS implementation effectiveness by internal (and external as needed) experts; e) assignment of an appropriately qualified staff member as overall E&S coordinator at Group level. Completon indicator: i) ESMS outline available; ii) full group level ESMS documents available and endorsed by CEO. | i) 2014-1-31 ii) 2014-4-30
3/PS2 | The Sponsor will update its HR policy documents and employee manual, to ensure that its labor practices and that of its contractors and sub-contractors comply with work force protection related requirements described in PS2. Completion indicator: updated HR policy documents and employee manual available. | 2014-01-31
4/PS2 | As part of its ESMS development process, Yoma will undertake an overall labor and working condition assessment against PS2 requirements, with a strong focus on worker housing conditions, oversight of contractor and sub-contractor labor practices, workforce protection, and occupational health and safety. The assesment will verify, among other things, that there are contract provisions between Yoma and contractors and sub-contractors requiring: contractor compliance with PS2 provisions on child labor, working hour, and working conditions; and that all employees be provided with housing of appropriate quality, as well as requiring submission of regular housing inspection reports and giving Yoma access to conduct random audits. Follow-up assessments will be performed when demolition and construction activities commence. Results from the assessment will provide input into Yoma’s ESMS development process. Completion indicator: PS2 assessment report available; Yoma group level minimum worker accommodation standards established. | 2014-04-30
5/PS3 | The Sponsor will ensure that design specifications of the diesel or LPG powered boilers to be installed at the Project site meet World Bank Group (WBG) Environmental Health and Safety (EHS) Guideline air emission limits before finalizing Project detailed designs. Completion indicator: boiler design specifications available. | Before finalizing Project detailed designs
6/PS3 | Yoma will develop a list of final Project resource efficiency measures to be adopted, and ensure their implementation. Related to this, the Company will also provide estimated annual energy and water consumption data and benchmarking performance data (as per Table 1 of the WBG EHS Guidelines for Tourism and Hospitality Development) specifically for the Business hotel. On the basis of estimated performance data and other relevant information, the Company will develop and implement technically and financially feasible measures for improving resource efficiencies of the Business Hotel. Completion indicator: i) final list of resource efficiency measures and estimation of expected energy/water/material savings available; ii) energy and water consumption and benchmarking data for the business hotel available. | i) 2014-4-30 ii) 2014-1-31
7/PS4 | The Sponsor will provide to IFC a “Life & Fire Safety (L&FS) Master Plan” (i.e. a set of documents including detailed design, specifications, and narrative descriptions) prepared by a qualified fire safety professional. The Master Plan will demonstrate that building design is consistent with requirements of local fire codes and one internationally accepted standard and which will identify major fire risks, applicable codes, standards and regulations, and mitigation measures. The Sponsor will undertake post-construction L&FS completion audits, prepared by a qualified fire safety engineer/auditor, to verify that buildings have been constructed in compliance with the Master Plan. Completion indicator: i) L&FS Master Plan available; ii) Post-construction L&FS completion audit report available. | i) 2 months before start of major structural works ii) Before opening of each building
8/PS4 | The Company will commission regular legionella tests of the hot water systems at Project facilities. Completion indicator: Test results available in Annual Monitoring Report submitted to IFC. | Annually