## Project ESAP Status Report
ESAP - Enel Wind #33579
Task Title/Description | Anticipated Completion Date
1.Enel Brasil Participacoes (EBP) will review its project screening and risk assessment procedure to ensure alignment with IFC’s Performance Standards. Additional project screening criteria will be added for biodiversity and avifauna, indigenous peoples, cumulative impacts and reputational risks. The alternatives analysis process for the overall location of the wind site and the design of the site will be also included as part of the screening process of new project sites. | 2014-03-31
2.EBP will review its procedure with respect to its acquisition of existing assets to ensure that E&S aspects are assessed and mitigations are prescribed in alignment with Performance Standards. | 2014-03-31
3.EBP will develop a procedure on the integration of social impacts into the risks and impacts identification process to further align with the Performance Standards. | 2014-03-31
4.Through the use of an external expert, EBP will conduct a rapid assessment on the potential cumulative impacts of current and future planned wind power developments on high-risk avifauna areas in Bahia. | 2014-12-01
5.EBP will develop a roadmap to implement a modification in the company structure so that it accommodates the establishment of an Environmental and Social Technical Management Function that works across functional units by overseeing and coordinating E&S aspects from the project’s inception and site selection to implementation and operation. | 2015-02-16
6.EBP will contract a senior-level Biodiversity Resource to act as an advisor to the Company on biodiversity issues, particularly on birds and bats. | 2014-04-30
7.EBP will develop and implement a Stakeholder Engagement Policy and Procedure, to be applied in all new projects. The Policy and Procedure will include provisions which are consistent with PS requirements, including PS 7, and will include the requirement and process for establishing a community grievance mechanism. | 2014-03-31
8.EBP will develop a workers grievance management procedure on the basis of Human Rights Policy's provisions, which will apply to unionized and non-unionized workers, including contracted workers. | 2014-03-31
9.EBP will develop a procedure on land acquisition and involuntary resettlement consistent with Performance Standard 5. | 2014-03-31
10.EBP will contract external experts to collect further data on the potential use of the Cristal and Serra Azul WPPs by migratory birds and bats and those that fly at collision height (e.g., soaring birds and insectivorous bats). A collision risk model (CRM) will be developed. | 2015-04-30
11.EBP will include a component on post-construction wildlife fatality monitoring in the Fauna Monitoring Program at Cristal and Serra Azul WPPs. A review of additional mitigation measures will be conducted based on the outcomes of the additional birds and bat studies and included amongst mitigation measures for fauna management. | 2015-04-30
12.EBP will install bird flight diverters on some of the above-ground transmission lines within the Cristal and Serra Azul WPPs based on an assessment | 2014-12-15