## Project ESAP Status Report
Environmental and Social Action Plan (ESAP)
Project Name: | Intermed
Team Name: | CM1C1
Country: | Mongolia
Project ID: | 33808
Task Title/Description | Anticipated Completion Date
1.Establish an overarching sustainability policy defining its objectives and principles that will guide the Company to achieve sound EHS performance of the Project – including compliance with the applicable local laws and regulations and the IFC Performance Standards | 2014-01-31
2. Review the applicable WBG EHS guidelines and modify as needed its EHS monitoring procedures to include all the parameters in those guidelines. | 2014-01-31
3.Include the necessary clauses in the contract with Element LLC, the licensed bio-hazardous waste management contractor to: (i) provide regulatory permits demonstrating its regulatory compliance, (ii) allow Intermed to annually review and audit Element LLC’s operations against a requirement checklist to ensure that they are meeting Intermed requirements on waste handling and disposal and (iii) require Element LLC to provide a complete chain of custody documentation (signed off at various check points) during day to day waste handling/disposal. | 2013-10-31
4.Provide to IFC a third-party certification from the competent professional that the new hospital was designed and constructed in full compliance with an internationally-accepted life and fire safety code (as referred in the ESAP #4 above) local building codes, local fire department regulations and local legal requirements | After completion of construction of the Hospital and prior to commencement of operations