## Sheet1
ESAP CRUSADER 34022
Assessment and Management of Environmental and Social Risks and Impacts
Sign on to a Health, Safety, Environment and Community (HSEC) Policy for Borborema that defines how the Company’s exploration project will be operated in line with the requirements of IFC’s Performance Standards, EHS Guidelines and Brazilian legislation appropriate to the level of activities. | Within 2 months of subscription.
Retain an experienced international ESHS consultant to satisfaction of IFC to support the company with:
a. Development of the necessary Elements/Programs and ESHS Management Plans/SOPs of the HSEC Policy for Borborema which are aligned with GIIP to address existing environmental, social and health and safety risks from current exploration activities. | Within 6 months of subscription.
b. Carry out an independent ESHS audit of existing operations at Posse to identify any gaps with IFC’s Performance Standards and EHS Guidelines with a focus on PS1 and pollution prevention aspects. | Provide IFC with a copy of the EHS Audit within 6 months of subscription.
Provide IFC with confirmation of the closure of identified gaps to IFC’s satisfaction within 12 months of subscription.
Disclose the HSEC Policy on Crusaders’ website | Within 2 weeks of IFC’s approval of the Policy
Environmental and Social Impact Assessment (ESIA)
Develop an ESIA for the Borborema Project in line with IFC’s Performance Standards, EHS Guidelines and GIIP. | 60 days prior to the start of construction
Organizational Capacity
Retain an in-house EHS Manager at the corporate level to support the development of the ESHS MS at Posse and the HSEC Policy at Borborema and build capacity with the local staff. | Within 6 months of subscription.
Stakeholder Engagement and Grievance Mechanism
Retain an experienced international social consultant to satisfaction of IFC to support the company with:
a. Develop a Stakeholder Engagement Plan and a Grievance Mechanism and Procedure for Posse and Borborema to identify/map key stakeholders and engage and communicate with the affected community and stakeholders in a frequent and effective manner. | Within 6 months of subscription
Land Acquisition and Compensation for Exploration
Develop a Land Use and Compensation Plan (LACP) for Borborema to outline the principles, guidelines and approaches that will be followed for land acquisitions and compensation activities in accordance with PS5 requirements. | Within 6 months of subscription
Human Resource Policy and Employee Grievance Mechanism
a. Develop a Human Resources Policy consistent with the requirements of PS 2 and disclose it on its website. | Within 6 months of subscription
b. Develop a Grievance Mechanism for workers in line with the requirements of PS2. | Within 6 months of subscription
Historic Heap Leach Pad
The Company will hire an independent consultant to carry out a Phase I and limited Phase II Site Investigation to determine any potential historic contamination of soil and/or ground water from the operation of the old heap leach pad. | Within 6 months of subscription
Transportation Management
Develop a Transportation Management Plan (TMP) for Posse to identify and manage and monitor risks for vehicular traffic related to the project and train personnel. | Within 6 months of subscription