## Sheet1
ESAP COLOMBIAN MINES 34112
Environmental and Social Management System
Sign on to a Health, Safety, Environment and Community (HSEC) Corporate and Site-Specific Policy that defines how the projects will be operated in line with the requirements of IFC’s Performance Standards, EHS Guidelines and Colombian legislation appropriate to the level of activities. | 2013-12-31
Retain an experienced international ESHS consultant to satisfaction of IFC to support the company with:
a. Development of the necessary Elements/Programs and ESHS Management Plans/SOPs of the HSEC Policy for El Dovio, Yarumalito and Mercedes which are aligned with GIIP to address existing environmental, social and health and safety risks form current exploration activities. | 2014-06-30
b. Develop a Grievance Mechanism for El Dovio, Mercedes and Yarumalito to address community concerns in line with PS1. | 2014-06-30
c. Design and implement a surface water participatory monitoring program to identify existing water quality and quantity conditions in the area, communicating these to the local population and to serve as baseline for the future ESIA. | When surface water baseline work begins as part of the ESIA for any of its Projects.
Disclose the HSEC Policy on Colombian Mines’ website | Within 2 weeks of IFC’s approval of the Policy.
Organizational Capacity
Retain an in-house E&S Specialist for El Dovio with experience in the application of GIIP to implement the HSEC Policy and build capacity with the local staff. | 2014-10-31
Stakeholder Engagement
Retain an experienced international social consultant to satisfaction of IFC to support the company with:
a. Development of a Stakeholder Engagement Plan (SEP), a Grievance Mechanism and Procedure for El Dovio, Mercedes and Yarumalito to identify/map key stakeholders and engage and communicate with the affected community and stakeholders in a frequent and effective manner. Reference: Stakeholder Engagement: A Good Practice Handbook for Companies Doing Business in Emerging Markets (May 2007); “Addressing Grievances from Project Affected Communities: Guidance for Projects and Companies on Designing Grievance Mechanisms”, IFC, 2009. | 2014-06-30
Land Acquisition and Compensation for Exploration
Develop a Land Use and Compensation Plan (LACP) for El Dovio, Mercedes and Yarumalito to outline the principles, guidelines and approaches that will be followed for land acquisitions and compensation activities in accordance with PS5 requirements. | 2014-06-30
Biodiversity Management
Retain an experienced and recognized biodiversity consultant to satisfaction of IFC to partner with a local biodiversity organization to:
a. Carry out a Rapid Biodiversity Assessment (RBA) of upcoming exploration activities at the El Dovio Concession. Conduct a Critical Habitat Assessment in line with PS6, develop management and mitigation measures for incorporation into the applicable Management Plans/Procedures. | 2014-06-30
b. Incorporation of Management and Mitigation Measures into Biodiversity Management Plans/Procedures. | 2014-08-29
Internationally Recognized Area
Contribute to a conservation program, as agreed on with relevant conservation organization, to promote or enhance to conservation aims and effective management of the Bosques Montanos del Sur de Antioquia area. | Agreement in place 3 months after exploration work begins at Yarumalito
Indigenous Peoples
Retain a consultant with experience in PS7 to satisfaction of IFC to:
a. Develop a Corporate Indigenous Peoples (IP) Consultation Framework to assure engagement with Indigenous and Afro Colombian Peoples within any of the Company’s concession is in line with PS7 requirements. | 2014-06-30