## Sheet1
Action | Deliverables | Due Date
1. The company will develop and implement a corporate Environmental and Social Management System (ESMS) policy and management system applicable to all installations, complementing existing aspects with additional ones in order to comply with IFC requirements, as described in the ESRS. | 1. Evidence of hiring a consultant acceptable to IFC to develop and implement a corporate ESMS. | 2014-02-01
| 2. Identification of key environmental aspects and occupational risks | 2014-06-01
| 3. Draft documentation of ESMP (plans and procedures) | 2014-12-01
| 4. Monitoring and reporting system created with defined indicators. | 2015-03-01
2. The company will develop and implement a corporate program of internal and external audits for environmental, occupational health and safety (OHS), and fire safety aspects to be applied to all existing assets, as described in the ESRS. | 1. Screening criteria for both newly constructed facilities and leased facilities. | 2014-03-01
| 2. Evidence of implementation of the screening framework | 2014-10-01
3. The company will complement the existing organizational capacity with someone centrally responsible at the corporate level, as described in the ESRS. | 1. Provide a copy of the organizational chart of Anima EHS department. | 2013-12-01
| 2. Provide a copy of the terms of employment of the new EHS Manager | 2014-01-01
4. The company will develop and implement an OHS management program to effectively address the risks of its operations (mainly the operation of laboratories and maintenance of facilities), as described in the ESRS. | 1. Identification of key occupational risks | 2014-06-01
| 2. Draft documentation of OHS management program (plans and procedures) | 2014-11-01
| 3. Monitoring and reporting system created with defined indicators. | Jan-15
5. Life and Fire Safety :
Life and Fire Safety System Design:
For all buildings scheduled for construction, engage professional services of a qualified Life and Fire Safety Engineer acceptable to IFC to prepare Master Plan (engineering design) and post construction inspections to verify that the system was installed as designed. Life and fire safety design shall be responsive to one international life safety code and the Brazilian life safety code. The design shall comply with the Life and Fire Safety requirements of the IFC General EHS Guideline. | 1. Signed contract for professional services to perform the Life and Fire Safety system design and post construction inspection and certification of as-built system. | Prior to start of construction activities in all projects
Certification of Life and Fire Safety System Design :
Provide third party certification by a qualified professional acceptable to IFC that the design and construction of life and fire safety systems for new constructions or renovations comply with the specifics of IFC life and fire safety guidelines. | 2. Certification prepared and submitted to IFC by the qualified professional engaged as described above. | Prior to start of construction activities in all projects
Certification of Life and Fire Safety System Construction :
A qualified professional acceptable to IFC shall provide a professional certification affirming that facility construction faithfully incorporates all elements of the life and fire safety design previously certified to IFC. | 3. Certification prepared and submitted to IFC by the qualified professional as described above. | On completion of construction activities in all projects
6. The company will expand the recycling program to all the campuses and will identify mechanisms to reduce the amount of waste generated, as well as reuse, recycle and dispose properly the waste. The program should include hazardous waste generated throughout the facilities including those from the labs. | 1. Solid waste register and implementation procedures developed. | 2014-03-01
| 2. Solid waste program implemented: records by site and type of waste. | 2014-08-01
7. Review, develop and implement emergency preparedness and response plans for all the facilities. The plans should include at least evacuation routes, training, fire drills, and use of emergency equipment. The plans should be communicated to employees, students, and community. | 1. Emergency preparedness and response plans/procedures.
| (a) 25% of facilities: | (a) May 2014
Where required, in the existing facilities, the company will enhance L&FS elements such as detection mechanisms, alarm systems, fire suppression systems, and emergency signage. | (b) 100% of the total facilities: | (b) Nov-14
| 2. Training and fire drills records, as well as photographic evidence of implementation of the plans. | 2015-01-01
| 3. Report of updates of life and fire safety mechanisms in the existing facilities. | 2015-02-01
8. The company will create and complement a formal internal and external grievance mechanisms : | 1. Grievance process in form and content acceptable to IFC. | 2014-08-01
i) For the employees to raise reasonable concerns, consistent with IFC’s Performance Standard 2. The grievance mechanism will be communicated to all the employees and for new employees it will be made available at the time of hire. | 2. Evidence of disclosure to company employees and its neighbors. | 2014-10-01
ii) For the neighbors, particularly with regards to receiving complaints, consistent with IFC’s Performance Standard 1.