## Project ESAP Status Report
Environmental and Social Action Plan (ESAP)
| Project Name: CMHL | Project ID: 35127
| Country: Myanmar | Sector: Retail
No. | Task Title/Description | Anticipated Completion Date
1/PS1 | The company will provide a status update on its initiative to develop a food safety management system based on principles of HACCP. | 2016-05-31
2/PS1 | The company will refine its E&S management system (ESMS) which will consist of: i) the company E&S policy; ii) appropriate Key Performance Indicators (KPI); iii) standard operating procedures (SOP) on pre-construction site E&S due diligence, life and fire safety, land acquisition and involuntary resettlement, EPR; labor and working conditions; contractor and supplier labor management; resource efficiency including refrigerant selection; and waste management; iv) a monitoring and reporting system whereby each property will regularly report performance data (according to aforementioned KPIs) to responsible E&S staff at the head office; v) a mechanism to regularly review ESMS implementation effectiveness. | 2016-03-31
3/PS1 | The company will set up a practicable system as part of its ESMS to screen primary suppliers for potential child and forced labor practices, and for potential impacts on biodiversity (primarily in relation to farms located in ecologically sensitive areas which may potentially entail significant conversion of natural or critical habitats), and address issues if found, to the extent that the company has commercial leverage over those primary suppliers. | 2016-03-31
4/PS2 | The company will review and refine its OHS related policies, and implement a system to monitor safety performance (including that related to road safety), conduct root cause analysis of accidents, and take corrective actions. | 2016-01-31
5/PS3 | For properties which discharge directly to surface water, and those that discharge into the sewer system of cities/towns which do not have a municipal WWTP, the company will commission tests of waste water levels (parameters: BOD, COD, oil and grease, total suspended solids, and coliform bacteria) by a qualified testing entity. It will propose corrective actions (including equipment/facility retrofit as needed, such as ensuring that sewers are sealed and putting in place separate storm water discharge systems where technically and financially feasible) should results exceed WBG EHS General Guideline levels. | 2016-03-31
6/PS3 | The company will undertake a review of the types and quantities of solid wastes (including food wastes) generated at its facilities including mapping of their destinations and handling methods in the form of an audit trail, and based on review results, develop a technically and financially feasible plan to reduce, reuse, and recycle solid wastes, in order to meet food processing industry waste generation benchmark levels (refer to Table 2 of the WBG EHS Guidelines for Food and Beverage Processing). | 2016-03-31
7/PS3 | City Mart will undertake an energy and water efficiency review at its product distribution centers and several other representative properties, and based on review results, identify technically and financially feasible options to meet industry resource efficiency benchmark levels (refer to Table 3 of the WBG EHS Guidelines for Food and Beverage Processing). | 2016-03-31
8/PS3 | The company will use an internationally recognized methodology to annually quantify total GHG emissions from its operations, and explore technically and financially feasible options for GHG reduction. | First instance 3/31/2016; thereafter annually
9/PS4 | The company will develop a corporate level Fire Directive and Master Plan which specifies minimum LFS requirements to be adopted by all new project designs. The Master Plan will identify major fire risks, applicable local and international fire codes, and mitigation measures, and will address the following LFS elements: fire prevention; means of egress; detection and alarm systems; compartmentation; fire suppression and control; emergency and response plan; and operation and maintenance. It will be reviewed and verified by a qualified LFS engineer, and its content will be consistent with the requirements of the local fire code and one internationally recognized LFS code (e.g. U.S. National Fire Protection Association or NFPA codes). | 2016-03-31
10/PS4 | Within three months of construction/refurbishment completion of the first two upcoming new projects, the company will commission L&FS post-construction completion audits by qualified LFS engineers, to verify that buildings have been constructed or refurbished in compliance with the Corporate Fire Directive and Master Plan. | Within 3 months of construction / refurbishment completion of first two upcoming new projects
11/PS4 | The company will put in place an appropriate system to regularly monitor potential fire risks. Completion indicator: annual internal monitoring reports available included in the AMR. | 2016-03-31